Scope of Work

Team Members: Matthew Mendenhall

Date Submitted for review: January 30th, 2026

Submitted to: UNMC Water, Climate and Health Group

Project Goals:

The goal of this project is to provide a detailed and statistical data analysis of air quality in Nebraska for the UNMC Water, Climate, and Health Group. The client has requested four key analyses: (1) Determine five locations in Nebraska with the highest mean and media concentrations of VOC, PM 2.5, and PM 10.0. (2) Take the data from the previous step and analyze them with certain days and locations with the highest maximum values. (3) Analyze how humidity and temperature effects air quality. The client uses specific categories and tables to identify humidity and temperature. (4) Look at any AQI health risks from the datasets of PM 2.5 and PM 10.0 based on the AQI ratings.

Project Tasks:

To achieve the project goals, I have identified the following key tasks needed to be completed.

Task 1: Determine locations with high mean and media concentrations of VOC, PM 2.5, and PM 10.0.

Data from the UNMC Water, Climate and Health Group will be extracted and organized into Excel for data processing in Python software development. The data in Python will be cleaned up and organized for certain categories. As a final deliverable, I will include the cleaned CSV file and the raw data Excel file.

Task 2: Use Python Software to organize and filter data

Python will be used to filter and gather data for analysis. I will use the pandas package to filter specific types of information requested by the client. Summarizing functions will be used to filter the categories from the previous task and include the mean and median numbers to create a code to deal with the maximum values on certain days and locations. As a final deliverable, I will provide both the Python script file (.py file) and annotated code document to the client.

Task 3: Use the resources provided to determine how temperature and humidity effect air quality

The client has provided important resources to determine the meaning of certain categories. The client provides an Air Purple Map data that provides data with certain filters that can be organized and edited. And I will also use the resources provided to discover the health risks of PM 2.5 and PM 10.0.

Task 4: Summarize the results of the data

Once the analysis has been completed, I will summarize all of the findings in a written report to be presented to the client at the end of this project. The written report will include a summary table of all the findings through the analysis.

Project Deliverables:

The deliverable and due dates for this project are summarized in the following table:

| Deliverable | Files Included | Due to Client by |
| --- | --- | --- |
| Raw Data File | CIVE202_Spring 2026_Matthew_Project1_RawData.csv | 2-4-26 |
| Python Code File | CIVE202_Spring 2026_Matthew_Project1_PythonCode.ipynb | 2-4-26 |
| GitHub Link | GitHub File | 2-4-26 |
| Annotated Code Document | CIVE202_Spring2026_Matthew_Project1_ACD.xlsx | 2-4-26 |
| Written Summary | CIVE202_Spring 2026_Matthew_Project1_FinalReport.docx | 2-4-26 |